## Index
NORTH COAL STATE OWNED CORPORATION
ERP FORMS & STANDARD TEMPLATES - PROCUREMENT MODULE
Developer pack accompanying the approved System Architecture & BPR Report (20 September 2026) ¦ Prepared by Crest Point Consulting Group ¦ Version 1.0
COLOUR LEGEND
Yellow | Field entered by a user (blue text = example data shown for illustration)
Grey | Auto-populated / auto-calculated by the system
Light grey | Not applicable on this form
Navy | Section / column headers and signature-block titles
Form Code | Sheet (click to open) | Purpose | Source in approved report
PC-01 | PC-01 Pending Request Queue | Queue of approved purchase requests with the ED approval gate | 4.6.2 Purchase Request Receipt
PC-02 | PC-02 Method & Classification | Procurement method and classification record | 4.6.2 Procurement Method Selection
PC-03 | PC-03 Bid Comparison | Competing bids and mandatory selection justification | 4.6.2 Bid Tracking and Supplier Selection Justification
PC-04 | PC-04 PO & Contract | Purchase order / contract record with deadline, alerts and deposit flag | 4.6.2 Purchase Order & Contract Recording
PC-05 | PC-05 Security Deposit Action | Deposit receipt, refund authorization and forfeiture | 4.6.2 Supplier Security Deposit Management
PC-06 | PC-06 Security Deposit Ledger | Active, refunded and forfeited deposits | 4.6.2; 4.6.4 Reports
PC-07 | PC-07 Implementation Tracker | Implementation % tracker with deadline alerts and Overdue / Breached flag | 4.6.2 Project Implementation Tracking
PC-08 | PC-08 Extension Request | Formal contract extension with mandatory justification | 4.6.2 Contract Extension Workflow
PC-09 | PC-09 Project Handover | Completion / handover record for non-goods contracts | 4.6.2 Goods Delivery, Project Handover
PC-10 | PC-10 IC Verification | Mandatory IC verify / reject at GRN or Handover | 4.6.2 IC Verification Gate; Workflow 4
PC-11 | PC-11 Contract Register | Register layout with summaries by method and status | 4.6.4 Required Reports
PC-12 | PC-12 Supplier Master | Supplier master with blacklist flag (addition) | 4.6.1 pain point - not in To-Be
PC-13 | PC-13 Classifications | Procurement classification settings | 4.6.2 Procurement Classification
PC-14 | PC-14 Thresholds Config | Procurement thresholds and authority limits with test calculator | 4.6.1 As-Is thresholds; 4.6.2
PC-15 | PC-15 Correction Request | Standard officer correction request (Procurement) | 4.6.2 Officer Correction Request Workflow
PC-16 | PC-16 Approval Matrix | Who prepares, approves and verifies each form | 4.6.3 System Roles and Access Permissions
PC-17 | PC-17 Accounting Entries | Deposit, goods received and payment entries | 4.6.4 Accounting Entries
PC-18 | PC-18 Reports Spec | Required procurement reports and filters | 4.6.4 Required Reports
DESIGN RULES THAT APPLY TO EVERY FORM
1. Single currency: Afghan Afghani (AFN) only.
2. The ERP does NOT run the procurement procedures: supplier selection, tendering, quotations and negotiation happen in hard copy outside the ERP and are referenced by document number. The ERP records the method, classification, bids, contract, deadlines, deposits and handover.
3. No purchase request is accessible to Procurement until the ED physical approval confirmation is recorded; requests without it stay in Pending ED Approval.
4. Internal Control verification is positioned strictly at the GRN or Project Handover stage; IC is otherwise read-only. Procurement forms therefore carry a "Verified by" block only on the handover and IC records.
5. The Executive Director and Directors have no system access; their approvals are physical and recorded by department staff. No ED / Director signature block appears on any printed form.
6. Officers can never edit or delete a submitted entry; corrections follow PC-15. Every action is written to the Control Log (layout FA-18 in the Finance workbook), which no user can alter.
7. Names, references, values and thresholds in these sheets are illustrative examples; threshold values come from the As-Is analysis and must be confirmed.

## PC-01 Pending Request Queue
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
PENDING PURCHASE REQUESTS QUEUE (ED APPROVAL GATE)
Real-time queue - a request is accessible to Procurement only after the ED physical approval confirmation is recorded
Purchase Request Ref. | Requesting Department | Item Description and Quantity Required | Date of Request | Dept Head Approval | Director Physical Approval Recorded | ED Physical Approval Confirmation Recorded | Queue Status (auto) | Accessible to Procurement Officer?
PR-2026-0312 | Inventory & Warehouse | Diesel fuel - generators; 10,000 litres | 2026-10-08 | Approved | Yes | Yes | Active queue | Yes
PR-2026-0318 | Properties | Roof repair materials - Block A; 1 lot | 2026-10-09 | Approved | Yes | No | Pending ED Approval | No - held
PR-2026-0321 | Administration | Office chairs; 20 pieces | 2026-10-12 | Approved | Yes | Yes | Active queue | Yes
PR-2026-0325 | Finance | Laptop computers; 3 pieces | 2026-10-13 | Approved | No | No | Pending ED Approval | No - held
Requests in active queue |  |  | 2
Requests held - Pending ED Approval |  |  | 2
NOTES FOR DEVELOPERS
1. Each request arrives with a notification and shows: reference, requesting department, item description and quantity, date of request, Department Head / Director approval status and ED approval status.
2. System gate: requests without the recorded ED physical approval confirmation are held in "Pending ED Approval" status and are NOT accessible to the Procurement Officer.
3. The Inventory section (4.2) lists only Department Head and Director approval before transfer, while this section requires the ED confirmation and the Finance section adds a budget check (FA-09). Confirm the single approval chain; the As-Is pain point "cumbersome pre-procurement approvals" is not reduced by the To-Be as written.
4. The Executive Director and Directors have no system access. Their purchase approval is obtained physically outside the ERP and recorded by department staff BEFORE the request reaches Procurement; no ED / Director signature block appears on these forms.

## PC-02 Method & Classification
[Corporation logo] | NORTH COAL STATE OWNED CORPORATION
PROCUREMENT METHOD AND CLASSIFICATION RECORD
Form PC-02 ¦ Version 1.0 ¦ Recorded by the Procurement Officer; the procurement procedures themselves run in hard copy outside the ERP
A. REQUEST AND METHOD
Purchase Request Ref. | PR-2026-0312 | Requesting Department | Inventory & Warehouse
Item Description and Quantity | Diesel fuel - generators; 10,000 litres | Estimated Value (AFN) | 420000
Procurement Method | Quotation-Based | Procurement Classification | Goods
B. THRESHOLD CHECKS (see PC-14)
Threshold-Suggested Method | Quotation-Based | Method Consistent with Threshold? | Yes
Approving Authority by Value | Executive Director | Authority Approval Ref. (if above ED limit) (addition - see note 3) | (not required at this value)
C. DOCUMENTS
Hard-Copy Document Ref. (tender / quotation file) | PROC-HC-2026-0188 | Recorded By (Procurement Officer) | PRC-OFF-01
Next Step | Record competing bids and written justification (PC-03), then the purchase order (PC-04)
RECORDED BY (Procurement Officer)
Name:
Position:
Signature:
Date:
NOTES FOR DEVELOPERS
1. Methods: Tender (high value), Quotation-Based (minimum three quotations, medium value), Direct Purchase (single supplier, low value). Classification defaults: Goods, Consultancy, Non-Consultancy, Construction; the Procurement Head can add, edit or disable classes (PC-13).
2. The approved report says thresholds are "defined" but gives no figures; PC-14 uses the As-Is values (quotations above AFN 20,000, ED authority to 5M, General Directorate to 35M, above that the National Procurement Authority). The consistency check is a suggested control, not an approved feature.
3. ADDITION TO CONFIRM: contracts above the ED limit need General Directorate or National Procurement Authority approval, but the To-Be records only the ED approval. The authority approval reference field is added to trace that hard-copy approval.
4. All tendering, quotation collection, evaluation and negotiation stay in hard copy outside the ERP and are referenced by document number.

## PC-03 Bid Comparison
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
BID COMPARISON AND SELECTION JUSTIFICATION
Form PC-03 ¦ Version 1.0 ¦ Mandatory for Tender and Quotation-Based purchases before the purchase order is finalized
A. REFERENCE
Purchase Request Ref. |  | PR-2026-0312 | Procurement Method | Quotation-Based
Classification |  | Goods | Minimum Bids Required (see note 2) | 3
Number of Bids Recorded |  | 4 | Lowest Eligible Bid (AFN) (Active suppliers only) | 420000
B. COMPETING BIDS
No. | Supplier Name | Bid Price (AFN) | Hard-Copy Document Ref. | Supplier Status (auto) | Price Rank (eligible)
1 | Example Supplier Co. | 420000 | PROC-HC-2026-0188/1 | Active | 1
2 | Example Supplier B | 445000 | PROC-HC-2026-0188/2 | Active | 3
3 | Example Supplier C | 438000 | PROC-HC-2026-0188/3 | Active | 2
4 | Example Barred Co. | 400000 | PROC-HC-2026-0188/4 | Blacklisted | Ineligible
5
6
C. SELECTION AND JUSTIFICATION
Winning Supplier |  | Example Supplier Co. | Winning Bid Price (AFN) | 420000
Winning Supplier Status |  | Active | Winner is the Lowest Bid? | Yes
Written Justification (mandatory) |  | Lowest evaluated price and full technical compliance with the fuel specification. EXAMPLE DATA.
Gate Result |  | READY - bid comparison complete; the purchase order may be finalized
RECORDED BY (Procurement Officer)
Name:
Position:
Signature:
Date:
NOTES FOR DEVELOPERS
1. The Officer records competing supplier names and submitted bid prices (AFN) and a mandatory written justification for the winning selection (e.g. lowest evaluated price, technical compliance). The system stores and displays this for transparency and audit visibility.
2. The approved report requires "minimum three quotations" for Quotation-Based purchases; it gives no minimum for Tenders (PC-14 parameter applies to both until confirmed).
3. ADDITION TO CONFIRM: the As-Is pain point "no vendor management system to flag blacklisted or barred companies" has no feature in the To-Be. The Supplier Status column and winner-eligibility check use the supplier master in PC-12 to cover it. Example Barred Co. shows a blacklisted bidder.

## PC-04 PO & Contract
[Corporation logo] | NORTH COAL STATE OWNED CORPORATION
PURCHASE ORDER / CONTRACT RECORD
Form PC-04 ¦ Version 1.0 ¦ Drafted by the Procurement Officer; approved by the Procurement Department Head; sent to the supplier in hard copy
A. ORDER DETAILS
PO / Contract Ref. (auto, sequential) | PO-2026-0051 | Date of Purchase Order (system date) | 2026-10-09
Purchase Request Ref. (linked) | PR-2026-0312 | Procurement Method | Quotation-Based
Supplier Name | Example Supplier Co. | Item / Project Description (from approved request) | Diesel fuel - generators
Quantity Approved in Request | 10000 | Quantity Ordered | 10000
Quantity Variance (auto) | 0 | Variance Note (mandatory if variance is not 0)
Unit Price (AFN) | 42 | Total Value (AFN) Quantity x Unit Price | 420000
Contract Deadline / Completion Date | 2026-10-31 | Custom Notification Threshold (days before deadline) | 7
Alert Date (auto) | 2026-10-24 | Delivery / Project Location | HQ Store
Security Deposit Required? | Yes | Required Deposit Amount (AFN) | 42000
Hard-Copy Document Ref. | PROC-HC-2026-0188 | ED / Director Approval Ref. (auto-linked from request) | DIR-APR-2026-0449
Status | Raised | Check | OK
B. APPROVAL
Procurement Dept Head Decision | Approved | Decision Date | 2026-10-09
Result | Finalized - purchase order sent to the supplier in hard copy outside the ERP; ERP keeps the digital record and status
PREPARED BY (Procurement Officer) |  | APPROVED BY (Procurement Department Head)
Name: |  | Name:
Position: |  | Position:
Signature: |  | Signature:
Date: |  | Date:
NOTES FOR DEVELOPERS
1. Status path: Raised -> Sent to Supplier -> Goods Received (set automatically when the Inventory GRN is confirmed) -> Completed (set automatically after IC verification). The Tracker may also flag a contract Overdue / Breached (PC-07).
2. Quantity comes from the approved request; any variance must be noted. Total value is auto-calculated and not editable. The custom notification threshold (e.g. 1 week, 2 months) drives the deadline alert.
3. Supplier Security Deposit: when "Yes" the required amount is recorded here and tracked through PC-05 / PC-06. ED approval is auto-linked from the purchase request.
4. The Executive Director and Directors have no system access. Their purchase approval is obtained physically outside the ERP and recorded by department staff BEFORE the request reaches Procurement; no ED / Director signature block appears on these forms.
Formulas:
PO-2026-0051 = [PO-2026-0051, row above]-[Quotation-Based, row above]

## PC-05 Security Deposit Action
[Corporation logo] | NORTH COAL STATE OWNED CORPORATION
SUPPLIER SECURITY DEPOSIT - RECEIPT, REFUND, FORFEITURE
Form PC-05 ¦ Version 1.0 ¦ Refund and forfeiture are authorized by the Procurement Department Head; Finance processes
A. DETAILS
Action Record No. | SDA-2026-000011 | Date | 2026-10-14
Contract Ref. | CT-2026-009 | Supplier | Example Consultant Ltd
Action | Refund authorization | Amount (AFN) | 40000
Deposit Required per Contract (AFN) | 40000 | Deposit Held Before Action (AFN) | 40000
Procurement Head Decision (refund / forfeiture) | Approved | Decision Date | 2026-10-14
Finance Processing Ref. (bank reconciliation / PV) | PV-000131 | Processed By (Finance Officer) | FIN-OFF-02
Reason / Breach Description (mandatory for forfeiture) | Contract successfully completed; handover verified by IC. EXAMPLE DATA.
B. AUTOMATIC ENTRY AND CHECKS
Accounting Entry | Dr Supplier Security Deposit (Current Liability) / Cr Bank Account
Amount Check | OK - within the deposit held
Posting Status | Authorized - system posts the entry automatically
AUTHORIZED BY (Procurement Department Head) |  | PROCESSED BY (Finance Officer)
Name: |  | Name:
Position: |  | Position:
Signature: |  | Signature:
Date: |  | Date:
NOTES FOR DEVELOPERS
1. Receipt: supplier pays into the corporate bank account; the Finance Officer confirms the deposit in bank reconciliation and links it to the specific contract. No Head authorization is needed for receipt.
2. Refund: after successful completion the Head authorizes release and Finance processes the payment. Forfeiture: on supplier breach the Head authorizes and the system recognizes the penalty as Other Income.
3. Deposits are held as Current Liabilities; forfeitures accrue to Other Income without manual Finance journals.

## PC-06 Security Deposit Ledger
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
SUPPLIER SECURITY DEPOSIT LEDGER
Report layout - active, refunded and forfeited deposits (forfeitures transferred to Other Income)
Contract Ref. | Supplier | Description | Deposit Required (AFN) | Received (AFN) | Refunded (AFN) | Forfeited to Other Income (AFN) | Balance Held (AFN) | Status (auto)
CT-2026-014 | Example Supplier Co. | Construction - warehouse extension | 150000 | 150000 | 0 | 0 | 150000 | Active - held
CT-2026-009 | Example Consultant Ltd | Consultancy - safety study | 40000 | 40000 | 40000 | 0 | 0 | Refunded
CT-2026-003 | Example Supplier B | Goods - spare parts | 60000 | 60000 | 0 | 60000 | 0 | Forfeited
PO-2026-0051 | Example Supplier Co. | Goods - diesel fuel | 42000 | 0 | 0 | 0 | 0 | Awaiting receipt
TOTAL |  |  | 292000 | 250000 | 40000 | 60000 | 150000
NOTES FOR DEVELOPERS
1. Deposits held are Current Liabilities (Dr Bank / Cr Supplier Security Deposit); refunds clear the liability; forfeitures move it to Other Income. Balance Held = Received - Refunded - Forfeited.
2. The deposit received for CT-2026-014 matches the AFN 150,000 "supplier security deposit" example in the Finance bank reconciliation sheet (FA-06).

## PC-07 Implementation Tracker
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
PROJECT IMPLEMENTATION TRACKER AND DEADLINE ALERTS
Form PC-07 ¦ Version 1.0 ¦ Large contracts (Construction, Consultancy) - updated by the Procurement Officer
Contract Ref. |  | CT-2026-014 | Supplier / Contractor | Example Supplier Co.
Contract Deadline |  | 2026-12-31 | Notification Threshold (days before deadline) | 30
Report As-of Date |  | 2026-10-14 | Classification | Construction
No. | Update Date | Implementation % | Basis (physical site report / milestone certificate ref.) | Updated By | Comment
1 | 2026-07-01 | 10% | Site report SR-2026-031 | PRC-OFF-01
2 | 2026-08-01 | 25% | Site report SR-2026-044 | PRC-OFF-01
3 | 2026-09-01 | 40% | Milestone certificate MC-2026-006 | PRC-OFF-01
4 | 2026-10-01 | 50% | Milestone certificate MC-2026-007 | PRC-OFF-01
5
6
7
8
TRACKER SUMMARY (auto)
Latest Implementation % |  | 50%
Days to Deadline |  | 78
Alert Date |  | 2026-12-01
Contract Status |  | On track
UPDATED BY (Procurement Officer) |  |  | ALERTS RECEIVED BY (Procurement Department Head)
Name: |  |  | Name:
Position: |  |  | Position:
Signature: |  |  | Signature:
Date: |  |  | Date:
NOTES FOR DEVELOPERS
1. The Officer periodically updates the implementation % (e.g. 25%, 50%, 75%) from physical site reports or milestone certificates. Automated alerts go to the Procurement Officer and Head when the deadline is near and the % is below 100%; a passed deadline flags the contract Overdue / Breached.
2. The alert threshold is the custom value set on the purchase order (PC-04). A formally approved extension (PC-08) updates the deadline and resets the alerts.

## PC-08 Extension Request
[Corporation logo] | NORTH COAL STATE OWNED CORPORATION
CONTRACT EXTENSION REQUEST
Form PC-08 ¦ Version 1.0 ¦ Initiated by the Procurement Officer; approved by the Procurement Department Head
Extension Request No. | EXT-2026-000007 | Date Raised | 2026-10-14
Contract Ref. | CT-2026-014 | Supplier / Contractor | Example Supplier Co.
Current Contract Deadline | 2026-12-31 | Proposed New Deadline | 2027-01-31
Extension Requested (days) | 31 | Implementation % at Request | 50%
Written Justification (mandatory) | Winter weather delays to concrete works; supplier requests 31 days. EXAMPLE DATA.
Procurement Head Decision | Approved | Decision Date | 2026-10-15
System Result | Contract deadline updated to 31-Jan-2027; automated alerts reset
REQUESTED BY (Procurement Officer) |  | APPROVED BY (Procurement Department Head)
Name: |  | Name:
Position: |  | Position:
Signature: |  | Signature:
Date: |  | Date:
NOTES FOR DEVELOPERS
1. Formal extension workflow: Officer enters the proposed new deadline and a mandatory written justification -> request goes to the Head -> on approval the system updates the contract deadline and resets the automated alerts. Every step is in the Control Log (FA-18).

## PC-09 Project Handover
[Corporation logo] | NORTH COAL STATE OWNED CORPORATION
PROJECT COMPLETION / HANDOVER RECORD (NON-GOODS CONTRACTS)
Form PC-09 ¦ Version 1.0 ¦ Recorded by Requesting Department staff for Consultancy / Construction / services
A. HANDOVER DETAILS
Handover Record No. | PH-2026-000009 | Date Recorded | 2026-10-06
Contract Ref. | CT-2026-009 | Supplier / Consultant | Example Consultant Ltd
Classification | Consultancy | Requesting Department | Planning & Policy
Project / Service Description | Mine safety consultancy study - final report delivered. EXAMPLE DATA.
Completion Date | 2026-10-05 | Implementation % at Handover | 100%
Completion / Milestone Certificate Ref. | MC-2026-011 | Supplier Invoice Ref. | INV-C-0231
Contract Value (AFN) | 800000 | Supplier Invoice Amount (AFN) | 800000
Recorded By (Requesting Dept staff) | PLN-OFF-02 | Status | Pending IC verification
Next Step | Routed to Internal Control for mandatory verification (PC-10) before any accounting entry is posted or payment cleared.
PREPARED BY (Requesting Department Staff) |  | REVIEWED BY (Requesting Department Head) | VERIFIED BY (Internal Control & Audit)
Name: |  | Name: | Name:
Position: |  | Position: | Position:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:
NOTES FOR DEVELOPERS
1. For non-goods contracts the requesting department - not Procurement - records the completion or handover. Goods are received by the Inventory department through the GRN (IN-05).
2. If Internal Control rejects, the Requesting Department Head unlocks the record, the staff corrects it and resubmits, the Head re-approves and it returns to IC.
3. Name, position and date may be pre-filled by the system from the Control Log; signatures are by hand so the printed form can be archived in the hard file.

## PC-10 IC Verification
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
INTERNAL CONTROL VERIFICATION - GRN OR PROJECT HANDOVER
Form PC-10 ¦ Version 1.0 ¦ The only mandatory IC gate in the Procurement module (goods version also at IN-06)
Verification No. |  | ICV-2026-000445 | Date Received by IC | 2026-10-07
Document Type |  | Project Handover | Document Ref. | PH-2026-000009
PO / Contract Ref. |  | CT-2026-009 | Re-verification Round | 1
Contract Value (AFN) |  | 800000 | Value Delivered / Completed (AFN) | 800000
Supplier Invoice Amount (AFN) |  | 800000 | Physical Delivery / Completion Confirmed by IC? | Yes
VERIFICATION CHECKS (system-assisted)
No. | Check |  |  | Result | IC Comment
1 | Delivered goods / completed milestones exactly match the physical reality |  |  | Yes
2 | Delivered / completed value exactly matches the supplier invoice |  |  | Yes
3 | Delivery / completion is consistent with the approved contract terms (value within contract) |  |  | Yes
Outcome (system rule) |  | VERIFY
Final Outcome (IC decision) |  | Verified | Decision Date | 2026-10-07
IC Comments (mandatory if Rejected)
If Rejected |  | Notification with IC comments to the Requesting Department Head -> Head unlocks -> staff corrects and resubmits -> Head re-approves -> back to IC
If Verified |  | PO / contract status -> Completed; system posts Dr Relevant Expense or Fixed Asset Account / Cr Accounts Payable; Finance receives the "Awaiting Payment" notification for the final supplier payment.
PREPARED BY (Inventory Officer / Requesting Dept Staff) |  |  | REVIEWED BY (Receiving Department Head) | VERIFIED BY (Internal Control & Audit)
Name: |  |  | Name: | Name:
Position: |  |  | Position: | Position:
Signature: |  |  | Signature: | Signature:
Date: |  |  | Date: | Date:
NOTES FOR DEVELOPERS
1. IC verifies physical delivery / project completion against the supplier invoice and the approved contract terms. Read-only access; Verify or Reject only, comments mandatory on rejection; every outcome goes to the Control Log (FA-18).
2. Where goods are received through a GRN, the same verification is shown in IN-06 and the Procurement module simply follows the resulting status.
3. Name, position and date may be pre-filled by the system from the Control Log; signatures are by hand so the printed form can be archived in the hard file.

## PC-11 Contract Register
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
PURCHASE ORDER / CONTRACT REGISTER
Report layout - status of every purchase order and contract
Date Range |  | 01-Jan-2026 to 31-Oct-2026 |  |  | Generated On / By | 14-Oct-2026 10:15 / PRC-HEAD-01
PO / Contract Ref. | Date | Purchase Request Ref. | Method | Classification | Supplier | Total Value (AFN) | Delivery Location | Status | Requesting Department
PO-2026-0045 | 2026-09-20 | PR-2026-0298 | Quotation-Based | Goods | Example Supplier Co. | 85000 | HQ Store | Goods Received | Inventory & Warehouse
PO-2026-0051 | 2026-10-09 | PR-2026-0312 | Quotation-Based | Goods | Example Supplier Co. | 420000 | HQ Store | Sent to Supplier | Inventory & Warehouse
CT-2026-014 | 2026-06-15 | PR-2026-0187 | Tender | Construction | Example Supplier Co. | 3000000 | HQ | Sent to Supplier | Properties
CT-2026-009 | 2026-05-02 | PR-2026-0120 | Quotation-Based | Consultancy | Example Consultant Ltd | 800000 | HQ | Completed | Planning & Policy
CT-2026-003 | 2026-02-10 | PR-2026-0044 | Tender | Goods | Example Supplier B | 2000000 | Second Unit A | Overdue / Breached | Inventory & Warehouse
TOTAL VALUE (AFN) | [5 empty] | 6305000
SUMMARY BY METHOD |  |  | Number | Total Value (AFN) |  |  | SUMMARY BY STATUS |  | Number
Tender |  |  | 2 | 5000000 |  |  | Raised |  | 0
Quotation-Based |  |  | 3 | 1305000 |  |  | Sent to Supplier |  | 2
Direct Purchase |  |  | 0 | 0 |  |  | Goods Received |  | 1
[7 empty] | Completed |  | 1
[7 empty] | Overdue / Breached |  | 1
NOTES FOR DEVELOPERS
1. Supports the reports on purchases by method (number and value), by classification, by supplier, by requesting department and by delivery location, and the status of all active purchase orders and contracts.
2. The four statuses in the approved design are Raised / Sent to Supplier / Goods Received / Completed; "Overdue / Breached" is the tracker flag from PC-07 and is shown here as a fifth status - confirm.

## PC-12 Supplier Master
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
SUPPLIER MASTER AND BLACKLIST REGISTER
Addition to the approved design - covers the "no vendor management system" pain point
ADDITION TO CONFIRM: the As-Is pain point asks for a database that records and flags blacklisted or barred companies, but the To-Be has no such feature. This layout is proposed; bid and winner eligibility checks in PC-03 read from it.
Supplier ID | Supplier Name | Contact Person | Phone | Address | Status | Reason / Hard-Copy Reference | Updated By
SUP-0001 | Example Supplier Co. | Example Contact 1 | +93 700 000 011 | Example address, Kabul | Active |  | PRC-OFF-01
SUP-0002 | Example Supplier B | Example Contact 2 | +93 700 000 012 | Example address, Kabul | Active |  | PRC-OFF-01
SUP-0003 | Example Supplier C | Example Contact 3 | +93 700 000 013 | Example address, Herat | Active |  | PRC-OFF-01
SUP-0004 | Example Barred Co. | Example Contact 4 | +93 700 000 014 | Example address, Kandahar | Blacklisted | Barred by decree DEC-2025-114 (example) | PRC-HEAD-01
SUP-0005 | Example Consultant Ltd | Example Contact 5 | +93 700 000 015 | Example address, Kabul | Active |  | PRC-OFF-01

## PC-13 Classifications
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
PROCUREMENT CLASSIFICATION SETTINGS
Maintained by the Procurement Department Head in system settings
No. | Classification | Type | Status | Changed On | Changed By
1 | Goods | Default | Active | 2026-01-01 | System
2 | Consultancy | Default | Active | 2026-01-01 | System
3 | Non-Consultancy | Default | Active | 2026-01-01 | System
4 | Construction | Default | Active | 2026-01-01 | System
5 | Equipment Lease (example) | Custom | Active | 2026-06-01 | PRC-HEAD-01
6
7
8
9
10
NOTES FOR DEVELOPERS
1. Only the Procurement Department Head can add, edit or disable classifications. Disabled classes stay on historical records. Every change goes to the Control Log (FA-18).

## PC-14 Thresholds Config
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
PROCUREMENT THRESHOLDS AND AUTHORITY LIMITS (PARAMETERS)
Parameter table - values from the As-Is analysis; confirm against Afghan public procurement rules for state-owned corporations
No. | Parameter | Value | Source | Notes
1 | Direct Purchase - upper limit (AFN) | 20000 | As-Is (inferred) | Purchases up to this value need no competing quotes; inferred from "three quotes above 20,000".
2 | Quotation-Based - applies above (AFN) | 20000 | As-Is | Minimum three quotations obtained from suppliers and compared.
3 | Tender threshold (AFN) |  | NOT STATED - confirm | The report says "defined tender threshold" but gives no figure. Leave blank until confirmed; the suggestion then never proposes Tender.
4 | Minimum number of quotations / bids | 3 | To-Be: "minimum three quotations" | Applied to Quotation-Based; assumed for Tender until confirmed.
5 | Cash payment applies below (AFN) | 50000 | As-Is | Cash for amounts under 50,000 AFN, bank transfer above. Applies to Finance payment mode.
6 | Executive Director authority - up to (AFN) | 5000000 | As-Is | Contracts up to this value are approved by the ED.
7 | General Directorate authority - up to (AFN) | 35000000 | As-Is | Above the ED limit and up to this value.
8 | National Procurement Authority - above (AFN) | 35000000 | As-Is | Contracts above the General Directorate limit.
TEST CALCULATOR
Contract value (AFN) |  | 420000
Suggested method |  | Quotation-Based
Approving authority |  | Executive Director
Payment mode (Finance) |  | Bank transfer
NOTES FOR DEVELOPERS
1. Rows 8-15 feed the consistency check on PC-02 and the minimum-bids rule on PC-03. They must be editable parameters (with effective dates in a real build) so procurement-rule changes need no code change.
2. The To-Be only ever records ED approval; it does not capture approval by the General Directorate or the National Procurement Authority for larger contracts (see PC-02 note 3).

## PC-15 Correction Request
[Corporation logo] | NORTH COAL STATE OWNED CORPORATION
OFFICER CORRECTION REQUEST - PROCUREMENT
Form PC-15 ¦ Version 1.0 ¦ Same standard form as FA-11, module set to Procurement
A. REQUEST (raised by Procurement Officer)
Request No. | CR-2026-000071 | Date Raised | 2026-10-09 14:20
Module | Procurement | Second Unit / HQ | HQ
Entry Type | Purchase Order / Contract | Entry Reference | PO-2026-0051
Raised By (Officer) | PRC-OFF-01 | Entry Status at Request | Submitted - before finalization
Description of Error (written justification) | Contract deadline entered as 31-Oct-2025; the contract states 31-Oct-2026. EXAMPLE DATA.
Required Correction | Change Contract Deadline to 31-Oct-2026.
B. PROCUREMENT DEPARTMENT HEAD DECISION (notified automatically on submission)
Decision | Approved | Decision Date / Time | 2026-10-09 15:00
Reason (recorded if Rejected)
Entry Unlocked | Yes - Officer notified automatically | Corrected Entry Ref. | PO-2026-0051 (rev. 2)
C. CONTROL LOG - PERMANENTLY RECORDED AND VISIBLE TO INTERNAL CONTROL
Original entry |  | Recorded
Correction request |  | Recorded
Department Head approval |  | Recorded
Corrected entry |  | Recorded
REQUESTED BY (Procurement Officer) |  | DECIDED BY (Procurement Department Head)
Name: |  | Name:
Position: |  | Position:
Signature: |  | Signature:
Date: |  | Date:
NOTES FOR DEVELOPERS
1. Applies to submitted records before finalization (e.g. wrong contract deadline, notification threshold or item description). The Officer can never modify or delete a submitted entry directly. An IC rejection at GRN / Handover uses the loop in PC-10. Every step is written to the Control Log.

## PC-16 Approval Matrix
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
PROCUREMENT APPROVAL AND VERIFICATION MATRIX
Who prepares, approves and verifies each form; the Executive Director has no system role
Form | Initiated / Prepared By | Department Head Action | ED / Director (physical, outside system) | Other Role | Internal Control (read-only) | Automatic System Action
PC-01 Pending Queue | Requesting department staff transfer approved request | Requesting Dept Head approved earlier | ED approval obtained outside, recorded by staff before transfer | None | Read-only | Holds requests without ED confirmation in Pending ED Approval
PC-02 Method & Classification | Procurement Officer | None (Head sets classifications) | None | None | Read-only | Threshold suggestion (recommended)
PC-03 Bid Comparison | Procurement Officer | None | None | None | Read-only | Stores bids and justification; supplier eligibility check (addition)
PC-04 PO & Contract | Procurement Officer drafts | Procurement Head approves and finalizes | ED approval auto-linked from request | None | Read-only | Auto total value; alert date; status Raised -> Sent
PC-05 Security Deposit | Finance confirms receipt; Procurement Head authorizes refund / forfeiture | Authorizes refund and forfeiture | None | Finance Officer confirms receipt / processes refund | Read-only | Posts deposit, refund or forfeiture entry
PC-07 Tracker / PC-08 Extension | Procurement Officer updates % / raises extension | Approves extension; receives alerts | None | None | Read-only | Alerts to Officer and Head; resets alerts on extension; flags Overdue / Breached
PC-09 Project Handover | Requesting Department staff | Requesting Dept Head reviews and re-approves after rejection | None | None | Mandatory Verify or Reject | Routes to IC
PC-10 IC Verification | n/a | Inventory Head or Requesting Dept Head unlocks on rejection | None | Finance receives Awaiting Payment | Verify / Reject at GRN or Handover | On verification: PO Completed; Dr Expense or Fixed Asset / Cr AP
PC-13 Classifications | Procurement Dept Head | Adds / edits / disables | None | None | Read-only | Logs every change
PC-15 Correction Request | Procurement Officer | Approves / rejects; unlocks if approved | None | None | Sees full trail in Control Log | Notifies Officer on unlock; logs every step

## PC-17 Accounting Entries
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
ACCOUNTING ENTRIES - DEVELOPER REFERENCE (PROCUREMENT)
Posted automatically in the background - no manual journal entries by Finance
# | Trigger Event | Debit | Credit | Posting Basis / Related Form
1 | Supplier security deposit received (confirmed by Finance) | Bank Account | Supplier Security Deposit Account (Current Liability) | Finance Officer confirms in bank reconciliation, linked to the contract (PC-05, FA-06)
2 | Supplier security deposit refunded (processed by Finance) | Supplier Security Deposit Account (Current Liability) | Bank Account | After Procurement Head authorization (PC-05)
3 | Supplier security deposit forfeited (approved by Procurement Head) | Supplier Security Deposit Account (Current Liability) | Other Income Account | After Procurement Head authorization (PC-05)
4 | Goods received / project completed (IC-verified GRN or Handover) | Relevant Expense or Fixed Asset Account | Accounts Payable | On IC verification (IN-05 / PC-09, PC-10)
5 | Final supplier payment processed by Finance | Accounts Payable | Bank Account | After the Awaiting Payment notification (FA-01)
NOTES FOR DEVELOPERS
1. The Procurement module itself posts nothing for purchase orders: financial effects arise only from Finance-confirmed deposits and IC-verified GRNs / Handovers. Deposits are classified as Current Liabilities; forfeitures accrue to Other Income (penalty revenue).
2. The goods-received entry is identical to the Inventory module entries (IN-13); the Inventory section splits it between expense and stock (asset) items. Confirm the final posting rule once to avoid double posting.

## PC-18 Reports Spec
[Corporation logo] |  | NORTH COAL STATE OWNED CORPORATION
REQUIRED REPORTS - PROCUREMENT
Every report is generated dynamically in real time with a flexible Custom Date Range filter; standard header/footer as FA-16
# | Report | Frequency | Filter Options | Export
1 | Bid Comparison and Selection Report | On demand | By contract: competing bids, prices and winning justifications | PDF + Excel
2 | Procurement Classification Report | On demand | By classification (Goods, Consultancy, Non-Consultancy, Construction, custom) | PDF + Excel
3 | Project Implementation & Deadline Tracker | Real-time | By implementation %, overdue contracts, extended contracts | PDF + Excel
4 | Security Deposit Ledger | On demand | Active deposits, refunded, forfeited (transferred to Other Income) | PDF + Excel
5 | Procurement Activity Report by Method | On demand | Tender / Quotation-Based / Direct Purchase; per period, per department, per Second Unit | PDF + Excel
6 | Purchase Order / Contract Register | On demand | By status, by supplier, by Second Unit | PDF + Excel
7 | Pending Purchase Requests Report | Real-time | All requests awaiting Procurement action | PDF + Excel
8 | Purchase Orders Awaiting Goods Receipt | Real-time | All finalized purchase orders pending IC-verified GRN / Handover | PDF + Excel
9 | Completed Procurements Report | On demand | All fully completed purchase cycles (per period, per supplier) | PDF + Excel
10 | Procurement Value by Method Report | Monthly / Annual | Total AFN value per procurement method in the defined period | PDF + Excel
11 | Supplier Purchase History Report | On demand | Per supplier: all purchase orders, values and delivery records | PDF + Excel
12 | Internal Control Verification Report | Monthly | By verification outcome (Verified / Rejected) at GRN / Handover stage | PDF + Excel
13 | Control Log / Audit Trail Report | On demand | By user, date and action type (including extension approvals and unlocks) | PDF + Excel